## Risk Register
KHAYA PAYROLL (PTY) LTD — CONSOLIDATED RISK REGISTER
POPIA (8 Conditions) + SOC 2 (CC1–CC9, A1) ¦ Version 1.0 ¦ Prepared for portfolio review
Risk ID | Risk Description | Source | Category | Likelihood (1–3) | Impact (1–3) | Inherent Risk Score | Current Controls | Control Effectiveness | Residual Risk Score | Treatment | Owner | Target Date | Status
R-001 | No Information Officer registered with the Information Regulator; no formal ownership of POPIA compliance obligations. | POPIA | Legal/Regulatory | 3 | 3 | 9 | CEO handles queries informally on an ad hoc basis. | Low | 8 | Mitigate | CEO / Incoming IO | Phase 1 | Open
R-002 | Over-collection of special personal information (medical/health data) for sick-leave documentation; no minimum-necessary standard defined. | POPIA | Legal/Regulatory | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer | Phase 2 | Open
R-003 | No documented legal basis mapping data categories to POPIA processing conditions (contract necessity, legal obligation, etc.). | POPIA | Legal/Regulatory | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer | Phase 2 | Open
R-004 | No privacy notice or disclosure process provided to client companies to inform employees of data collection purpose and retention period. | POPIA | Legal/Regulatory | 3 | 2 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer | Phase 2 | Open
R-005 | No data retention policy; former employee records persist indefinitely with no defined deletion or archival trigger. | POPIA | Operational | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | Information Officer / IT Head | Phase 2 | Open
R-006 | No Data Processing Agreements (DPAs) with third-party sub-processors (Intercom, SendGrid, Payment Gateway); further processing risk unmanaged. | POPIA | Legal/Regulatory | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | CEO / Information Officer | Phase 1 | Open
R-007 | No validation step for sensitive data field updates (banking details, ID numbers); mispayments and fraudulent updates may go undetected. | POPIA | Operational | 2 | 3 | 6 | Employees and HR admins update fields via self-service portal with no secondary confirmation. | Low | 5 | Mitigate | IT Head | Phase 2 | Open
R-008 | No Record of Processing Activities (ROPA); employees unaware of data subject rights (access, correction, objection). | POPIA | Legal/Regulatory | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | Information Officer | Phase 2 | Open
R-009 | Single-factor authentication only (username/password); no MFA, no encryption confirmed on sensitive fields; broad unlogged internal admin access to all client data. | POPIA | Technical | 3 | 3 | 9 | Username/password authentication in place. | Low | 8 | Mitigate | IT Head | Phase 2 | Open
R-010 | No documented incident response plan or breach notification procedure; no defined internal escalation path or 72-hour notification benchmark. | POPIA | Operational | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | Information Officer / IT Head | Phase 1 | Open
R-011 | No defined data subject request process; requests to access, correct, or delete personal information go unmet with no defined owner or timeline. | POPIA | Legal/Regulatory | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | Information Officer | Phase 2 | Open
R-012 | No security-specific governance structure; no security policy, no assigned security ownership beyond informal CEO involvement. | SOC 2 | Operational | 3 | 3 | 9 | CEO handles security queries informally. | Low | 8 | Mitigate | CEO / Information Officer | Phase 1 | Open
R-013 | No anonymous internal reporting channel for suspected security issues; no external responsible disclosure policy or security@ contact point. | SOC 2 | Operational | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer | Phase 1 | Open
R-014 | No formal, repeatable risk assessment process; risk reviews are reactive and ad hoc rather than proactive and scheduled. | SOC 2 | Operational | 3 | 2 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer / IT Head | Phase 3 | Open
R-015 | No mechanism to verify that controls are functioning as intended over time; controls could silently decay without detection. | SOC 2 | Operational | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | Information Officer / IT Head | Phase 3 | Open
R-016 | No formally adopted policies or procedures; all assessment recommendations remain unadopted suggestions without CEO sign-off. | SOC 2 | Operational | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | CEO / Information Officer | Phase 2 | Open
R-017 | No device offboarding procedure; departing staff laptops not consistently returned or wiped; no building access controls. | SOC 2 | Technical | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | IT Head | Phase 2 | Open
R-018 | No automated monitoring or alerting for suspicious activity; no vulnerability scanning; incident response plan untested. | SOC 2 | Technical | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | IT Head | Phase 1 / Phase 2 | Open
R-019 | No formal change management process; code pushed to production without peer review, testing, approval, or documented revert plan. | SOC 2 | Technical | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | IT Head | Phase 1 / Phase 2 | Open
R-020 | No vendor register or certificate renewal tracking; no business continuity plan, manual payroll fallback, or client communication plan. | SOC 2 | Operational | 3 | 3 | 9 | No formal control in place. | Low | 8 | Mitigate | Information Officer / IT Head | Phase 1 / Phase 2 | Open
R-021 | No SLA defined with clients; no uptime monitoring; no capacity planning to manage infrastructure growth. | SOC 2 | Operational | 2 | 3 | 6 | No formal control in place. | Low | 5 | Mitigate | IT Head | Phase 2 / Phase 3 | Open

## Legend
RISK REGISTER — LEGEND & SCORING GUIDE
── INHERENT RISK SCORE ── | Likelihood (1–3) × Impact (1–3) = 1–9
1–2 ● Low | Green — monitor; no urgent action
3–4 ● Low-Medium | Yellow — schedule remediation
5–6 ● Medium-High | Orange — priority remediation required
7–9 ● High | Red — immediate action required
── LIKELIHOOD ── | 1 = Low ¦ 2 = Medium ¦ 3 = High
── IMPACT ── | 1 = Low ¦ 2 = Medium ¦ 3 = High
── TREATMENT OPTIONS ──
Mitigate | Implement controls to reduce likelihood or impact
Accept | Acknowledge risk; no action taken (low residual risk)
Transfer | Shift risk to a third party (e.g. insurance, vendor SLA)
Avoid | Eliminate the activity that generates the risk
── STATUS ──
Open | Risk identified; remediation not yet started
In Progress | Remediation underway
Closed | Control implemented; risk remediated or accepted
── SOURCES ──
POPIA | Protection of Personal Information Act, No. 4 of 2013
SOC 2 | AICPA Trust Services Criteria — Security + Availability
── OWNERSHIP ──
Information Officer (IO) | CEO (interim, per CC1/Condition 1 recommendation)
IT Head | Senior engineering/technical lead — owns technical controls